## Chronologie du projet
CHRONOLOGIE DU PROJET
| ENTRER LA DATE DE DÉBUT : | 2017-07-19
ID | ACTIVITÉ | DÉBUT | FIN | REMARQUES
1 | Début du projet | 2017-07-17 |  | Penser à des questions chaques semaines
2 | Rapport | 2017-07-17 | 2017-07-31
3 | View Acceuil | 2017-07-31 | 2017-08-06
4 | View Comptes | 2017-07-31 | 2017-08-06
5 | View Jouer | 2017-07-31 | 2017-08-06
6 | BDD Création | 2017-08-07 | 2017-08-13 | Description/ et view description
7 | Comptes/se connecter | 2017-08-07 | 2017-08-13
8 | Concept Avatar | 2017-08-07 | 2017-08-13
9 | Menu Vue d'ensemble | 2017-08-07 | 2017-08-13
10 | Mode Classique | 2017-08-21 | 2017-09-04
11 | Mode Compet | 2017-08-21 | 2017-09-04
12 | Système Guilde | 2017-08-21 | 2017-09-04
13 | amis/stats | 2017-09-04 | 2017-09-11
14 | Succès/Titres/View | 2017-09-04 | 2017-09-11
15 | Implémentation Avatars | 2017-09-04 | 2017-09-11
16 | Tuto | 2017-09-04 | 2017-09-11
17 | Event | 2017-09-04 | 2017-09-11
18 | Comptes/Ladder | 2017-09-04 | 2017-09-11
19 | Design | 2017-09-04 | 2017-09-11
20 | Maap | 2017-09-04 | 2017-09-11
21 | Rapport Finale | 2017-09-04 | 2017-09-11
22 | Implémentation Avatars | 2017-09-04 | 2017-09-11
| Fin du projet | 2017-08-31

## calculs (hidden)
*** Cette feuille doit rester masquée ***
|  | Aujourd’hui : | 2017-07-22
5
#N/A
#N/A
#N/A
|  | Fenêtre Activités : | 8 | #N/A
|  |  | 9 | #N/A
|  |  | 1 | #N/A
#N/A
#N/A
#N/A
|  |  |  | 2 | #N/A
|  |  |  | 3 | 2
|  |  |  | 4 | 3
|  |  |  | 5 | 4
|  |  |  | 6 | 5
|  |  |  | 7 | 6
|  |  |  | 8 | 7
|  |  |  | 9 | 8
|  |  |  | #N/A | 9
|  | Calcul fenêtre de début | 2017-07-19
|  | Décalage | 0
|  | Début | 2017-07-19
|  | Fenêtre | 30
Position | Série | ID d’activité | Activité | 2017-07-19 | 2017-07-20 | 2017-07-21 | 2017-07-22 | 2017-07-23 | 2017-07-24 | 2017-07-25 | 2017-07-26 | 2017-07-27 | 2017-07-28 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18
11.3 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
10.3 | 2 | 2 | Rapport | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
9.3 | 3 | 3 | View Acceuil | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8.3 | 4 | 4 | View Comptes | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7.3 | 5 | 5 | View Jouer | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.3 | 7.3 | 7.3 | 7.3 | 7.3 | 7.3 | 7.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6.3 | 6 | 6 | BDD Création | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | #N/A | #N/A | #N/A | #N/A | #N/A
5.3 | 7 | 7 | Comptes/se connecter | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | #N/A | #N/A | #N/A | #N/A | #N/A
4.3 | 8 | 8 | Concept Avatar | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | #N/A | #N/A | #N/A | #N/A | #N/A
3.3 | 9 | 9 | Menu Vue d'ensemble | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2017-07-19 | 2017-07-20 | 2017-07-21 | 2017-07-22 | 2017-07-23 | 2017-07-24 | 2017-07-25 | 2017-07-26 | 2017-07-27 | 2017-07-28 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 2 | RAPPORT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 3 | VIEW ACCEUIL | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 4 | VIEW COMPTES | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 5 | VIEW JOUER | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 6 | BDD CRÉATION | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.3 | #N/A | #N/A | #N/A | #N/A
|  | 7 | COMPTES/SE CONNECTER | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.3 | #N/A | #N/A | #N/A | #N/A
|  | 8 | CONCEPT AVATAR | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3 | #N/A | #N/A | #N/A | #N/A
|  | 9 | MENU VUE D'ENSEMBLE | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3 | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2017-07-19 | 2017-07-20 | 2017-07-21 | 2017-07-22 | 2017-07-23 | 2017-07-24 | 2017-07-25 | 2017-07-26 | 2017-07-27 | 2017-07-28 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17
|  |  | Aujourd’hui | #N/A | #N/A | #N/A | 5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2017-07-01 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | juil 2017 -Bande supérieure | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2017-08-01 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  |  | août 2017 -Bande supérieure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
|  |  | 2017-07-02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2017-08-02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  |  | 3 | MER | JEU | VEN | SAM | DIM | LUN | MAR | MER | JEU | VEN | SAM | DIM | LUN | MAR | MER | JEU | VEN | SAM | DIM | LUN | MAR | MER | JEU | VEN | SAM | DIM | LUN | MAR | MER | JEU
|  |  |  | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
|  |  |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17